## Sheet1
Risk | Description | Probability | Impact | Responsibility | Response | Proposed Mitigation | Risk Level
lose aws keypair | unable to connect to instances and will have to start again | medium | medium | group | make sure to not delete the one in use | keep backup just incase | 6 |  |  | SEVERITY
Data is breached | Can lead to security breach which could allow attackers to view private data. | medium | low | group and aws | create secret variables for database uri and secret keys. | none | 2 |  |  | Minimal | Minor | Moderate | Major | Severe
lose internet access | lose internet acces during deployment of app which could cause errors during deployment | high | low | internet | move to a room with better wifi connection while the instance is running. | Have everything loaded and open before presentation | 6 | LIKELIHOOD | Guaranteed | 5 | 10 | 15 | 20 | 25
Lose all the files | Lose the files that contain my whole project | low | low | technical issues | uploaded everything to github so I will always have a backup online | consistently save and upload my files to github | 4 |  | Expected | 4 | 8 | 12 | 16 | 20
The re-rendering from react causes everything to slow down or stop working completely | the re-rendering in the background could cause the pc to slow down or stop working completely | high | medium | technical issues | has worked fine so far but keep close everything else in the background that is not required | keep another person's one running just incase during the presentation. | 12 |  | Likely | 3 | 6 | 9 | 12 | 15
pushing credentials to github | pushing files to git could cause us to accidentally push secret credentials to github whihc can be accessed by anyone | medium | high | group | make sure not to add secret keys onto files | add the secret keys to a git-ignore file or through jenkins secret keys | 15 |  | Possible | 2 | 4 | 6 | 8 | 10
rds instance goes offline | incase the rds instanced goes offline then the frontend and backend will not be able to access the data | medium | high | group and aws | could be because we uploaded endpoint and password to github, or an issue with aws | dont upload rds password and endpoint anywhere and keep a backup rds just incase | 12 |  | Unlikely | 1 | 2 | 3 | 4 | 5
eye and backstrain | too much sitting and looking at computer screen all day could cause eye and backstrain | high | low | group | take constant breaks | ensure everyone takes a break every hour or two | 10